## API Data
API TESTING STATUS REPORT - DATA ENTRY
Report Period: | Week of Jan 19-22, 2026
API Test Lead: | Chhavi Park
Lead Email: | Chhavi.park@company.com
API TEST SUITES SUMMARY
Test Suite | Total Tests | Passed | Failed | Blocked | Pass Rate % | Status
Authentication API | 156 | 152 | 0 | 1 | 97 | Stable
Payment Processing | 289 | 268 | 0 | 3 | 92 | Monitor
Inventory Management | 198 | 187 | 0 | 2 | 94 | Stable
Reporting Engine | 204 | 182 | 0 | 4 | 89 | Monitor
TOTALS | 847 | 789 | 0 | 10 | 93
DEFECT BREAKDOWN BY PRIORITY
Priority | Count | Status
Critical | 2 | Resolved
High | 8 | In Progress
Medium | 22 | Scheduled
Low | 16 | Backlog
AUTOMATION COVERAGE BY AREA
Area | Coverage %
Authentication | 90
Payment | 85
Inventory | 60
Inventory 2 | 60
Reporting | 75
RISKS & HIGH PRIORITY ISSUES
Issue ID | Description | Priority | Assigned Owner | Target Date
API-001 | Payment Gateway: Multi-currency edge cases failing | HIGH | Michael Chen | Jan 15
API-002 | Reporting Engine: Performance degradation >500 req/s | HIGH | David Park | Jan 16
API-003 | Authentication: Session timeout edge case | MEDIUM | Michael Chen | Jan 11

## Web Data
WEB TESTING STATUS REPORT - DATA ENTRY
Report Period: | Week of Jan 19-22, 2026
UI Test Lead: | Chhavi Park
Lead Email: | Chhavi.park@company.com
WEB TEST SUITES SUMMARY
Test Suite | Total Tests | Passed | Failed | Blocked | Pass Rate % | Status
Login & Auth Flow | 78 | 76 | 0 | 0 | 97 | Stable
Checkout Flow | 92 | 78 | 0 | 2 | 85 | Monitor
Product Search | 68 | 61 | 0 | 2 | 90 | Good
Dashboard & Reports | 82 | 65 | 0 | 3 | 79 | Action
TOTALS | 320 | 280 | 0 | 7 | 88
DEFECT BREAKDOWN BY PRIORITY
Priority | Count | Status
Critical | 2 | Resolved
High | 4 | In Progress
Medium | 10 | Scheduled
Low | 5 | Backlog
AUTOMATION COVERAGE BY AREA
Area | Coverage %
Login & Auth | 99
Checkout Flow | 77
Checkout Flow 2 | 77
Product Search | 44
Dashboard | 55
RISKS & HIGH PRIORITY ISSUES
Issue ID | Description | Priority | Assigned Owner | Target Date
SEL-001 | Checkout Flow: UI elements not rendering on Safari | HIGH | Jessica Martinez | Jan 14
SEL-002 | Dashboard: Data table pagination failing in Firefox | MEDIUM | Robert Thompson | Jan 20
SEL-003 | Mobile Responsive: Button alignment issue on Android | MEDIUM | Jessica Martinez | Jan 22